Quality Management Plan

Carbon Capture & Storage (CCS) Research Initiative

| Project Title | CCS Research Initiative |
| --- | --- |
| Document Version | 1.0 |
| Prepared By | HARISSA RANIA — Project Manager |
| Date | January 2025 |
| Applicable Standards | ISO 9001:2015, ISO 27914:2017, ASTM D1622 |
| Status | Active |

# 1. Purpose & Scope

This Quality Management Plan (QMP) defines the quality standards, assurance activities, and control processes that will be applied throughout the CCS Research Initiative. It ensures that all project deliverables — technical, documentary, and process-related — meet defined standards and are fit for purpose.

The QMP applies to all phases of the project including bench-scale R&D, geological storage assessment, pilot plant construction and operation, HSE compliance, and final reporting.

# 2. Quality Objectives

- Achieve CO2 capture efficiency of >=90% at pilot scale

- Maintain sorbent regeneration energy penalty <=3.5 GJ/tonne CO2

- Deliver all phase reports peer-reviewed and publication-ready

- Ensure zero non-conformances in regulatory submissions

- Complete all HSE activities with zero lost-time incidents (LTI)

- Maintain all experimental data with full traceability and audit trail

# 3. Quality Standards

| Standard | Applies To | Requirement |
| --- | --- | --- |
| ISO 9001:2015 | Overall project management | Quality management system; document control; corrective action process |
| ISO 27914:2017 | Geological CO2 storage | Site characterization, risk assessment, storage integrity monitoring |
| ASTM D1622 | Sorbent density measurement | Standardized method for apparent density of rigid cellular plastics |
| GLP (Good Lab Practice) | All bench-scale experiments | Documented protocols, traceable measurements, calibrated instruments |
| HAZOP (IEC 61882) | Pilot plant commissioning | Systematic hazard identification before commissioning |
| ISO 14001:2015 | Environmental management | Minimize environmental impact; EIA aligned with this standard |
| PMBOK 7th Ed. | Project management | PM processes, documentation, stakeholder engagement |

# 4. Quality Assurance Activities

## 4.1 Experimental Data Quality

- All lab instruments calibrated before each experimental campaign (record calibration certificates in SharePoint)

- Every experiment follows a written protocol (SOP) approved by the R&D Lead

- Duplicate or triplicate measurements required for all critical data points

- Raw data recorded in tamper-evident lab notebooks; digitized within 24 hours

- Independent data verification: second team member checks analysis results

## 4.2 Document Quality

- All deliverable documents peer-reviewed by at least one other team member before submission

- Document version control enforced: naming convention [Code]_[Type]_v[X.X]_[YYYYMMDD]

- Phase gate reports reviewed by Sponsor before approval

- Final feasibility report undergoes external peer review (academic partner)

## 4.3 Engineering Quality

- Pilot plant design reviewed by independent EPC contractor before construction

- HAZOP conducted by certified facilitator with full core team attendance

- All punch list items from commissioning closed before trial operations begin

- Pressure vessels and pipework inspected to local regulatory standards

# 5. Quality Control Checkpoints

| Checkpoint | What is Checked | Who Checks | When | Pass Criterion |
| --- | --- | --- | --- | --- |
| Sorbent data QC | Capture efficiency measurements | R&D Lead | After each experiment set | CV <5% across replicates |
| Instrument calibration | GC, FTIR, pressure sensors | Lab Tech | Before each campaign | Within manufacturer tolerance |
| Phase report review | Technical accuracy, completeness | PM + Lead | Before gate review | No major errors; sponsor approves |
| HAZOP sign-off | All hazard actions closed | HSE Officer | Pre-commissioning | Zero critical open items |
| Pilot data QC | Continuous capture efficiency | Process Eng. | Weekly during trial | Weekly avg >=88% |
| EIA review | Regulatory completeness | HSE Officer + PM | Before submission | Regulator accepts without major queries |
| Final report review | Integrated findings, accuracy | All Leads + External | Month 17 | External peer reviewer approves |

# 6. Non-Conformance Management

A non-conformance (NC) is any situation where a deliverable, process, or result does not meet the defined quality standard. The NC process is:

- Identify: Any team member identifies and records the NC in the NC Log (SharePoint)

- Classify: PM classifies severity — Minor (no impact on project), Major (affects deliverable quality), Critical (affects safety or regulatory compliance)

- Investigate: Root cause analysis completed within 48 hours by the relevant lead

- Correct: Corrective action implemented; affected work re-done or re-tested

- Verify: PM or Lead verifies correction is effective

- Close: NC logged as closed with evidence; lessons captured

Critical NCs are escalated to the Project Sponsor and, if safety-related, to the HSE Officer for stop-work assessment.

# 7. Quality Roles & Responsibilities

| Role | Quality Responsibility |
| --- | --- |
| Project Manager | Owns this QMP; ensures quality activities are resourced and executed; manages NC log; reports quality status in monthly dashboard |
| R&D Lead | Ensures GLP compliance for all experiments; approves SOPs; reviews experimental data before reporting |
| Process Engineer | Ensures engineering quality standards are met; leads HAZOP; manages punch list |
| HSE Officer | Ensures HSE-related quality; manages EIA quality; verifies all safety procedures are followed |
| Lab Technicians | Execute experiments per approved SOPs; record data accurately; report anomalies immediately to R&D Lead |
| All Team Members | Responsible for quality of their own work; raise quality concerns immediately; participate in peer reviews |

# 8. Quality Metrics & Reporting

- Number of open non-conformances — reported monthly in project dashboard

- Percentage of experimental data sets passing QC on first attempt — target >95%

- Number of document revision cycles before approval — target <2 rounds

- HAZOP actions closed on time — target 100%

- Calibration compliance rate — target 100%

# 9. Document Control

| Document Owner | Project Manager |
| --- | --- |
| Review Frequency | At each phase gate |
| Storage Location | SharePoint > CCS Project > Quality Management |
| Next Review | August 2025 (Phase 1 Gate) |