Project Status Report

Carbon Capture & Storage (CCS) Research Initiative

| Report Period | [Month X] — [Date Range] |
| --- | --- |
| Reporting PM | HARISSA RANIA |
| Project Phase | [Current Phase] |
| Report Number | SR-00X |
| Next Report Due | [Date] |
| Distribution | Project Sponsor, Core Team, HSE Officer |

# 1. Overall RAG Status

| Scope | Schedule | Budget | Risk |
| --- | --- | --- | --- |
| Green | Amber | Green | Green |

RAG Key: Green = On track | Amber = At risk, action in place | Red = Off track, immediate action required

# 2. Executive Summary

[2–3 sentence high-level summary of overall project health, major achievements this period, and any issues requiring Sponsor attention.]

# 3. Key Achievements This Period

- [Deliverable or milestone completed — e.g., Sorbent screening report finalized]

- [Another achievement — e.g., Permit application submitted to regulator]

- [Another achievement — e.g., Phase 1 gate review approved by Sponsor]

- [Another achievement]

# 4. Schedule Status

| Milestone | Planned Date | Forecast Date | Actual Date | Status |
| --- | --- | --- | --- | --- |
| Kick-off meeting | Jan 2025 | Jan 2025 | Jan 2025 | Done |
| Phase 1 gate review | Aug 2025 | Aug 2025 | — | On Track |
| Geological survey complete | Oct 2025 | Nov 2025 | — | At Risk |
| Phase 2 gate review | Mar 2026 | Mar 2026 | — | On Track |
| Final feasibility report | Jun 2026 | Jun 2026 | — | On Track |

# 5. Budget Status

| Phase / Area | Budget ($) | Spent to Date ($) | Remaining ($) | Variance |
| --- | --- | --- | --- | --- |
| 1.0 Initiation & Planning | $120,000 | $[X] | $[X] | [+/-X%] |
| 2.0 Phase 1 — Bench R&D | $480,000 | $[X] | $[X] | [+/-X%] |
| 3.0 Phase 2 — Pilot Plant | $1,100,000 | $[X] | $[X] | [+/-X%] |
| 4.0 Geological Survey | $350,000 | $[X] | $[X] | [+/-X%] |
| 5.0 HSE & Compliance | $150,000 | $[X] | $[X] | [+/-X%] |
| 6.0 Closeout | $200,000 | $[X] | $[X] | [+/-X%] |
| TOTAL | $2,400,000 | $[X] | $[X] | [+/-X%] |

# 6. Active Risks & Issues

| ID | Description | Level | Trend | Update / Action |
| --- | --- | --- | --- | --- |
| R-01 | Sorbent degradation risk | High | Stable | Ongoing 500-hr stability test — Week 3 of 12 complete |
| R-03 | Geological site suitability | Medium | Improving | Second candidate site identified; survey scheduled Mo 6 |
| R-07 | Capture efficiency below 90% | High | Stable | Current bench results: 87% — optimization trial planned |
| [New] | [Add new risk here] | [Level] | [Trend] | [Action and owner] |

# 7. Planned Activities Next Period

- [Activity 1 — e.g., Complete CO2 capture experiment runs (sets 3–5)]

- [Activity 2 — e.g., Submit EIA draft for internal review]

- [Activity 3 — e.g., Procure pilot plant heat exchanger]

- [Activity 4]

# 8. Decisions / Approvals Required

| Decision Required | Decision Owner | Required By |
| --- | --- | --- |
| [Decision 1 — e.g., Approve sorbent selection for Phase 2] | Project Sponsor | [Date] |
| [Decision 2 — e.g., Authorize drawdown of contingency reserve] | Project Sponsor | [Date] |
| [Add more as needed] |  |  |

# 9. Issues Log

| ID | Issue Description | Raised By | Owner | Resolution / Status |
| --- | --- | --- | --- | --- |
| I-01 | [Issue description] | [Name] | [Owner] | [Resolution and current status] |
| I-02 | [Issue description] | [Name] | [Owner] | [Resolution and current status] |

# 10. Sign-Off

| Prepared by (PM) | [Signature] ___________________ Date: ________ |
| --- | --- |
| Reviewed by (Sponsor) | [Signature] ___________________ Date: ________ |