PROJECT CHARTER

Carbon Capture & Storage (CCS) Research Initiative

| Project Title | Carbon Capture & Storage (CCS) Research Initiative |
| --- | --- |
| Project Manager | HARISSA RANIA |
| Start Date | January 2025 |
| End Date | June 2026 |
| Duration | 18 months |
| Total Budget | RINGGIT MALAYSIA RM2,400,000 |
| Team Size | 12 FTEs (cross-functional) |
| Status | Planning Phase |
| Version | 1.0 — Initial Charter |
| Date Prepared | May 2025 |

# 1. Project Overview

| Total Budget | Duration | Team Size | CO₂ Target |
| --- | --- | --- | --- |
| RM2.4M RINGGIT MALAYSIA | 18 mo Jan 2025 – Jun 2026 | 12 Cross-functional | 500 t Capture capacity / yr |

## 1.1 Project Purpose

To research, design, and validate a pilot-scale Carbon Capture & Storage (CCS) system capable of capturing CO₂ from a simulated flue gas stream using amine-based chemical absorption, with the goal of informing a future commercial-scale deployment decision.

# 2. Objectives

- Evaluate and select the optimal CO₂ absorbent (amine, ionic liquid, or MOF)

- Design and construct a bench-scale capture unit (Phase 1)

- Scale to a pilot plant with ≥90% CO₂ capture efficiency (Phase 2)

- Assess geological storage site suitability via seismic & core analysis

- Conduct environmental impact and regulatory feasibility assessment

- Deliver a go/no-go recommendation for commercial scale deployment

# 3. Project Scope

## 3.1 In Scope

- Literature review and sorbent screening

- Bench-scale and pilot-scale capture testing

- Geological site survey and storage capacity modelling

- Health, Safety & Environment (HSE) assessment

- Regulatory review and Environmental Impact Assessment (EIA)

- Economic feasibility model (levelized cost of capture)

## 3.2 Out of Scope

- Full commercial plant construction

- CO₂ utilization or conversion research

- Transportation pipeline design

# 4. Assumptions & Constraints

## 4.1 Key Assumptions

- Access to a simulated flue gas stream at the test facility is available throughout the project

- Regulatory permits are obtained within 90 days of project start

- A geological survey partner is identified by Month 3

- No major scope changes occur after the Phase 1 gate review

## 4.2 Constraints

- Budget is fixed at RM2.4M — contingency reserve capped at 10%

- Team capacity is limited to 12 FTEs across all departments

- The pilot storage site must comply with ISO 27914 (CO₂ geological storage)

- Research findings must be suitable for publication in peer-reviewed journals

# 5. Key Deliverables

| # | Deliverable | Phase | Due |
| --- | --- | --- | --- |
| D-01 | Sorbent selection report | Phase 1 | Month 8 |
| D-02 | Bench-scale test data & analysis | Phase 1 | Month 8 |
| D-03 | Pilot plant design & commissioning report | Phase 2 | Month 15 |
| D-04 | Geological storage feasibility report | Geo. Survey | Month 14 |
| D-05 | Environmental Impact Assessment (EIA) | HSE & Compliance | Month 16 |
| D-06 | Final CCS feasibility & go/no-go report | Closeout | Month 18 |

# 6. Success Criteria

| Criterion | Target / Threshold |
| --- | --- |
| CO₂ capture efficiency at pilot scale | ≥ 90% |
| Levelized cost of capture | ≤ RM60 / tonne CO₂ |
| Lost-time incidents (LTI) | Zero — zero tolerance policy |
| Phase gate reviews approved on schedule | ≥ 90% milestones on time |
| Budget variance | ≤ ±5% of approved budget |
| Geological storage capacity confirmed | ≥ 1 Mt CO₂ |
| Sorbent regeneration energy penalty | ≤ 3.5 GJ / tonne CO₂ |
| Sorbent cycle lifetime | ≥ 1,000 cycles |

# 7. Project Team & Roles

| Role | Responsibilities | Interest | Influence |
| --- | --- | --- | --- |
| Project Manager | Overall coordination & delivery | High | High |
| R&D Lead (Chemistry) | Sorbent selection & bench testing | High | High |
| Process Engineer | Pilot plant design & scale-up | High | High |
| Geoscience Engineer | Geological site survey & storage | High | Medium |
| HSE Officer | Safety compliance & risk management | Medium | High |
| Sponsor / Exec | Budget approval & strategic direction | Medium | Very High |
| Regulatory Authority | Environmental permits & ISO compliance | Low | Very High |
| Community Officer | Local community liaison | Low | Medium |

# 8. Charter Approval

By signing below, the signatories confirm their understanding of and commitment to the project objectives, scope, budget, and schedule as described in this charter.

| Role | Name | Signature & Date |
| --- | --- | --- |
| Project Manager | _________________________ | _________________________ |
| Project Sponsor / Exec | _________________________ | _________________________ |
| R&D Lead | _________________________ | _________________________ |