## Stakeholder Register
CCS Research Initiative — Stakeholder Register
Interest & Influence scored 1–5 (5=highest). Priority Score = Interest × Influence.
ID | Stakeholder | Role / Title | Organization | Interest | Influence | Impact | Attitude | Engagement Strategy | Priority
S-01 | Project Sponsor | VP Research & Technology | Internal | 5 | 5 | 5 | Supportive | Monthly dashboard; gate review chair; go/no-go decision authority | 25
S-02 | Project Manager | Project Manager | Internal | 5 | 5 | 5 | Supportive | Full project authority; chairs all meetings; manages all comms | 25
S-03 | R&D Lead | Senior Research Chemist | Internal | 5 | 4 | 5 | Supportive | Daily standup; sorbent selection lead; co-author phase reports | 20
S-04 | Process Engineer | Senior Process Engineer | Internal | 5 | 4 | 5 | Supportive | Daily standup; pilot plant design and commissioning lead | 20
S-05 | Geoscience Engineer | Geoscience Specialist | Internal | 4 | 3 | 4 | Supportive | Weekly update; geological survey lead; monthly storage report | 12
S-06 | HSE Officer | Health, Safety & Environment Officer | Internal | 3 | 4 | 4 | Neutral | Bi-weekly safety review; mandatory sign-off before commissioning | 12
S-07 | Lab Technicians (x3) | Research Technician | Internal | 4 | 2 | 3 | Supportive | Daily R&D standup; clear test protocols provided | 8
S-08 | Procurement Officer | Procurement Specialist | Internal | 3 | 3 | 3 | Neutral | Engage early for equipment; weekly updates during Phase 2 | 9
S-09 | Regulatory Authority | Environmental Regulator | Government | 2 | 5 | 5 | Neutral | Formal permit submissions; quarterly regulatory briefings | 10
S-10 | Geological Survey Partner | Survey Contractor | External | 4 | 3 | 4 | Supportive | Monthly coordination call; shared data repository access | 12
S-11 | EPC Contractor | Engineering Contractor | External | 3 | 3 | 4 | Supportive | Weekly progress meetings during Phase 2 construction | 9
S-12 | Local Community | Community Representatives | Public | 2 | 3 | 3 | Skeptical | Quarterly public briefing; transparent safety communications | 6
S-13 | Academic Partner | University Research Lab | External | 3 | 2 | 3 | Supportive | Share bench data; co-publish findings; quarterly update | 6
S-14 | Finance Department | Finance Controller | Internal | 2 | 3 | 2 | Neutral | Monthly budget report; flag variances >5% immediately | 6
ATTITUDE: Supportive = Champions the project ¦ Neutral = Neither for nor against ¦ Skeptical = May resist
PRIORITY: 20–25 = Manage Closely ¦ 12–19 = Keep Satisfied/Informed ¦ 1–11 = Monitor only

## RACI Chart
CCS Research Initiative — RACI Chart
R = Responsible A = Accountable C = Consulted I = Informed (Each task must have exactly ONE A)
Task / Deliverable | Project Sponsor | Project Manager | R&D Lead | Process Engineer | Geoscience Engineer | HSE Officer | Lab Techs | Procurement | Regulator | EPC Contractor
PHASE 1 — INITIATION & PLANNING
Develop project charter | A | R | C | C | I | I | I | I | I | I
Conduct literature review | I | A | R | C | C | I | C | I | I | I
Regulatory mapping & permit application | I | A | C | I | I | C | I | I | R | I
Vendor & partner selection | A | R | C | C | C | I | I | R | I | C
Initial risk register | I | R | C | C | C | C | I | I | I | I
Stakeholder analysis & RACI | A | R | C | I | I | I | I | I | I | I
PHASE 2 — BENCH-SCALE R&D
Sorbent screening & selection | I | A | R | C | I | I | R | I | I | I
Bench-scale column setup | I | A | C | R | I | C | R | C | I | I
CO2 capture experiments | I | I | A | C | I | I | R | I | I | I
Sorbent regeneration testing | I | I | A | R | I | I | R | I | I | I
Analytical equipment commissioning | I | A | C | R | I | C | R | C | I | I
Phase 1 gate review & report | A | R | C | C | I | I | I | I | I | I
PHASE 3 — PILOT PLANT SCALE-UP
Pilot plant engineering design | I | A | C | R | I | C | I | C | I | R
Equipment procurement | I | A | I | C | I | I | I | R | I | C
Construction & commissioning | I | A | I | R | I | C | I | C | I | R
3-month pilot capture trial | I | A | R | R | I | C | R | I | I | I
HAZOP & HSE audit | I | C | C | C | I | R | I | I | I | C
Phase 2 gate review & report | A | R | C | C | I | C | I | I | I | I
PHASE 4 — GEOLOGICAL STORAGE
3D seismic survey | I | A | I | I | R | I | I | I | C | C
Core & well analysis | I | A | I | I | R | I | I | I | C | I
CO2 plume migration simulation | I | C | C | C | R | I | I | I | I | I
Storage feasibility report | A | C | C | I | R | I | I | I | C | I
PHASE 5 — HSE & COMPLIANCE
Environmental Impact Assessment | I | A | C | C | C | R | I | I | C | I
HSE compliance audit | I | A | I | C | I | R | I | I | C | I
Regulatory submission & liaison | I | R | I | I | I | C | I | I | A | I
PHASE 6 — CLOSEOUT
Economic model & cost analysis | A | R | C | C | C | I | I | I | I | I
Final feasibility report | A | R | R | R | R | C | I | I | I | I
Go/No-Go stakeholder presentation | A | R | C | C | C | C | I | I | I | I
Project closeout & lessons learned | I | R | C | C | C | C | I | I | I | I
LEGEND
R — Responsible: Does the work
A — Accountable: Owns the outcome (one per task)
C — Consulted: Provides input before task is done
I — Informed: Notified when task is complete