## Product Backlog
CCS Research Initiative — Product Backlog
Story Points use Fibonacci scale (1,2,3,5,8,13). Priority: Critical > High > Medium > Low
Epic ID | Sprint | User Story | Acceptance Criteria | Story Points | Priority | Status | Assigned To | Phase | Category
EPIC 1 — PROJECT INITIATION (Sprint 1)
E1-S1 | Sprint 1 | As a PM, I want a signed project charter so that the project has formal authorization | Charter includes scope, objectives, budget, team, and sponsor signature | 3 | Critical | Done | PM | Phase 1 | Governance
E1-S2 | Sprint 1 | As the team, I want a comprehensive literature review so we understand the CCS landscape | Min 30 sources; covers amine, MOF, ionic liquid sorbents; summarized in report | 5 | Critical | Done | R&D Lead | Phase 1 | Research
E1-S3 | Sprint 1 | As the PM, I want regulatory permits mapped so we avoid compliance delays | All required permits listed with timeline; regulatory contact identified | 3 | Critical | Done | PM | Phase 1 | Compliance
E1-S4 | Sprint 1 | As the PM, I want a risk register so we proactively manage threats | Min 8 risks identified; each has probability, impact, mitigation, owner | 2 | High | Done | PM | Phase 1 | Risk
E1-S5 | Sprint 1 | As the team, I want a RACI chart so roles are unambiguous | All 30+ tasks assigned; every task has exactly one Accountable owner | 2 | High | Done | PM | Phase 1 | Governance
EPIC 2 — BENCH-SCALE R&D (Sprints 2–4)
E2-S1 | Sprint 2 | As R&D Lead, I want sorbent screening complete so we select the best CO2 absorbent | Min 4 sorbents tested; capture efficiency, cost, stability documented; 1 selected | 8 | Critical | In Progress | R&D Lead | Phase 2 | R&D
E2-S2 | Sprint 2 | As Process Eng., I want a bench-scale absorption column built and operational | Column installed; safety checks done; first test run completed | 8 | Critical | In Progress | Process Eng. | Phase 2 | Engineering
E2-S3 | Sprint 3 | As R&D Lead, I want CO2 capture experiments completed | Min 20 experimental runs; capture efficiency data at 3 temps & pressures | 13 | Critical | To Do | R&D Lead | Phase 2 | R&D
E2-S4 | Sprint 3 | As R&D Lead, I want sorbent regeneration energy penalty quantified | Energy consumption per cycle measured; degradation curve plotted over 200 cycles | 8 | High | To Do | R&D Lead | Phase 2 | R&D
E2-S5 | Sprint 4 | As PM, I want a Phase 1 gate report approved by the sponsor | Report includes results, sorbent selection rationale, go/no-go recommendation | 5 | Critical | To Do | PM | Phase 2 | Governance
EPIC 3 — GEOLOGICAL STORAGE (Sprints 3–6)
E3-S1 | Sprint 3 | As Geoscience Eng., I want 3D seismic data acquired at candidate site | Full seismic survey dataset acquired; processed to interpretable format | 13 | Critical | To Do | Geoscience Eng. | Phase 4 | Geology
E3-S2 | Sprint 4 | As Geoscience Eng., I want core & well analysis completed | Porosity, permeability, caprock integrity data from min 2 appraisal wells | 8 | Critical | To Do | Geoscience Eng. | Phase 4 | Geology
E3-S3 | Sprint 5 | As Geoscience Eng., I want a CO2 plume migration model built | Numerical simulation shows CO2 stays within permitted boundary for 100 years | 8 | High | To Do | Geoscience Eng. | Phase 4 | Geology
E3-S4 | Sprint 6 | As PM, I want a storage feasibility report confirming site suitability | Report confirms >=1 Mt storage capacity; approved by Sponsor | 5 | Critical | To Do | Geoscience Eng. | Phase 4 | Governance
EPIC 4 — PILOT PLANT SCALE-UP (Sprints 5–8)
E4-S1 | Sprint 5 | As Process Eng., I want a pilot plant engineering design complete | Full P&ID, equipment list, layout drawing; reviewed by EPC contractor | 13 | Critical | To Do | Process Eng. | Phase 3 | Engineering
E4-S2 | Sprint 5 | As Procurement, I want all pilot plant equipment procured | All 6 major equipment items on order with confirmed lead times | 8 | Critical | To Do | Procurement | Phase 3 | Procurement
E4-S3 | Sprint 6 | As Process Eng., I want the pilot plant constructed and HAZOP complete | Plant built to spec; HAZOP signed off by HSE Officer; no critical actions open | 13 | Critical | To Do | Process Eng. | Phase 3 | Engineering
E4-S4 | Sprint 7 | As R&D Lead, I want 3-month pilot capture trial completed | Continuous operation for 90 days; >=90% CO2 capture efficiency achieved | 13 | Critical | To Do | R&D Lead | Phase 3 | R&D
E4-S5 | Sprint 8 | As PM, I want Phase 2 gate review approved | Pilot results presented; go/no-go decision from sponsor documented | 5 | Critical | To Do | PM | Phase 3 | Governance
EPIC 5 — HSE & COMPLIANCE (Sprints 6–8)
E5-S1 | Sprint 6 | As HSE Officer, I want an EIA submitted to regulators | Full EIA document submitted; regulator acknowledgement received | 8 | Critical | To Do | HSE Officer | Phase 5 | Compliance
E5-S2 | Sprint 7 | As HSE Officer, I want a full HSE compliance audit completed | Audit report with zero critical findings; corrective actions tracked | 5 | High | To Do | HSE Officer | Phase 5 | Compliance
E5-S3 | Sprint 8 | As PM, I want all regulatory conditions satisfied | All permit conditions closed out; confirmation from regulator received | 5 | Critical | To Do | PM | Phase 5 | Compliance
EPIC 6 — CLOSEOUT & REPORTING (Sprints 8–9)
E6-S1 | Sprint 8 | As PM, I want an economic model showing levelised cost of capture | LCOC <=60 USD/tonne; NPV analysis at 3 scale scenarios included | 8 | Critical | To Do | PM | Phase 6 | Finance
E6-S2 | Sprint 9 | As Sponsor, I want a final CCS feasibility report | Integrates all phase findings; min 50 pages; peer-reviewed quality | 13 | Critical | To Do | PM | Phase 6 | Governance
E6-S3 | Sprint 9 | As Sponsor, I want a go/no-go decision package for the board | Slide deck + executive summary; presented in board meeting | 5 | Critical | To Do | PM | Phase 6 | Governance
E6-S4 | Sprint 9 | As PM, I want project closeout completed | Lessons learned documented; assets handed over; team released | 3 | Medium | To Do | PM | Phase 6 | Governance
TOTAL STORY POINTS |  |  |  | 190

## Sprint Plans
CCS Research Initiative — Sprint Plans
Each sprint = 4 weeks. 9 sprints covering 18-month project. Velocity target: 25–35 story points per sprint.
Sprint | Duration | Theme | Key Deliverables | Story Points | Status
Sprint 1 ¦ Mo 1–2 ¦ Theme: Project Initiation ¦ Story Points: 15 ¦ Status: Done
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T1-01 | E1 | Draft & circulate project charter | PM | 16 | 16 | Done | Critical | Sponsor sign-off received
T1-02 | E1 | Conduct literature review (30+ sources) | R&D Lead | 24 | 24 | Done | Critical | Report filed in SharePoint
T1-03 | E1 | Regulatory mapping & permit application | PM | 12 | 10 | Done | Critical | Permits received Mo 2
T1-04 | E1 | Stakeholder analysis & RACI chart | PM | 8 | 8 | Done | High | Reviewed by Sponsor
T1-05 | E1 | Risk register v1 workshop | PM + Team | 6 | 6 | Done | High | 8 risks identified
T1-06 | E1 | Communication plan finalized | PM | 4 | 4 | Done | Medium | Distributed to all stakeholders
Sprint 2 ¦ Mo 3–4 ¦ Theme: Sorbent Screening & Bench Setup ¦ Story Points: 29 ¦ Status: In Progress
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T2-01 | E2 | Procure sorbent samples (MEA, MDEA, MOF, IL) | R&D Lead | 8 | — | In Progress | Critical | 4 sorbents ordered
T2-02 | E2 | Design bench-scale absorption column | Process Eng. | 16 | — | In Progress | Critical | P&ID drafted
T2-03 | E2 | Install GC & FTIR analytical instruments | Lab Tech | 12 | — | To Do | High | Equipment on order
T2-04 | E2 | Develop experimental protocol for sorbent tests | R&D Lead | 8 | — | To Do | High | Draft v1 ready
T2-05 | E2 | Initial sorbent CO2 uptake screening | R&D Lead | 20 | — | To Do | Critical | Bench column needed first
T2-06 | E1 | Submit regulatory permit application update | PM | 4 | — | To Do | High | 3-month check-in
Sprint 3 ¦ Mo 5–6 ¦ Theme: Capture Experiments & Seismic Survey ¦ Story Points: 29 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T3-01 | E2 | Run CO2 capture experiments (set 1: temperature) | R&D Lead | 24 | — | To Do | Critical | 20 runs planned
T3-02 | E2 | Run CO2 capture experiments (set 2: pressure) | R&D Lead | 24 | — | To Do | Critical | Parallel with set 1
T3-03 | E2 | Begin sorbent regeneration cycle testing | R&D Lead | 16 | — | To Do | High | Target: 200 cycles
T3-04 | E3 | Mobilize seismic survey team to site | Geoscience Eng. | 8 | — | To Do | Critical | Contractor mobilization
T3-05 | E3 | Acquire 3D seismic dataset | Geoscience Eng. | 40 | — | To Do | Critical | 4-week field campaign
T3-06 | E1 | Monthly sponsor dashboard report | PM | 4 | — | To Do | High | Months 5 & 6
Sprint 4 ¦ Mo 7–8 ¦ Theme: Phase 1 Gate & Core Analysis ¦ Story Points: 26 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T4-01 | E2 | Complete regeneration testing (200 cycles) | R&D Lead | 16 | — | To Do | Critical | Energy penalty quantified
T4-02 | E2 | Finalize sorbent selection report | R&D Lead | 8 | — | To Do | Critical | Board: MEA recommended
T4-03 | E2 | Phase 1 gate report drafting | PM + R&D | 12 | — | To Do | Critical | Due end Mo 8
T4-04 | E2 | Phase 1 gate review with sponsor | PM | 4 | — | To Do | Critical | Go/No-Go decision
T4-05 | E3 | Process & interpret seismic data | Geoscience Eng. | 32 | — | To Do | Critical | External lab processing
T4-06 | E3 | Core sampling — appraisal well 1 | Geoscience Eng. | 24 | — | To Do | High | Drill contractor engaged
Sprint 5 ¦ Mo 9–10 ¦ Theme: Pilot Plant Design & Procurement ¦ Story Points: 29 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T5-01 | E4 | Complete pilot plant engineering design (P&ID) | Process Eng. | 32 | — | To Do | Critical | EPC contractor review
T5-02 | E4 | Issue equipment RFQs and evaluate bids | Procurement | 16 | — | To Do | Critical | 6 major items
T5-03 | E4 | Place equipment purchase orders | Procurement | 8 | — | To Do | Critical | Long-lead items first
T5-04 | E3 | Build CO2 plume migration simulation model | Geoscience Eng. | 24 | — | To Do | High | Reservoir simulator
T5-05 | E3 | Seismic interpretation & storage capacity calc | Geoscience Eng. | 16 | — | To Do | High | Structural trap mapped
T5-06 | E1 | Update risk register (all active risks) | PM | 4 | — | To Do | High | Mo 9 update
Sprint 6 ¦ Mo 11–12 ¦ Theme: Construction & EIA ¦ Story Points: 34 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T6-01 | E4 | Site preparation & civil works | EPC Contractor | 40 | — | To Do | Critical | PM oversight
T6-02 | E4 | Equipment delivery & installation | Process Eng. | 32 | — | To Do | Critical | On-site supervision
T6-03 | E5 | Prepare & submit Environmental Impact Assessment | HSE Officer | 32 | — | To Do | Critical | Regulatory deadline
T6-04 | E3 | Finalize storage feasibility report | Geoscience Eng. | 16 | — | To Do | Critical | Sponsor approval required
T6-05 | E1 | Community quarterly briefing | PM | 4 | — | To Do | Medium | Public meeting
T6-06 | E5 | Prepare HAZOP study documentation | HSE Officer | 12 | — | To Do | High | Pre-commissioning req.
Sprint 7 ¦ Mo 13–14 ¦ Theme: Commissioning & Pilot Trial ¦ Story Points: 31 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T7-01 | E4 | Conduct HAZOP study with full team | HSE Officer | 16 | — | To Do | Critical | External facilitator
T7-02 | E4 | Commission pilot plant systems | Process Eng. | 32 | — | To Do | Critical | Punch list closure
T7-03 | E4 | Start 3-month continuous capture trial (Day 1) | R&D Lead | 8 | — | To Do | Critical | Target >=90% efficiency
T7-04 | E4 | Monitor daily pilot plant operations | Lab Techs | 80 | — | To Do | Critical | Shift rota in place
T7-05 | E5 | HSE compliance audit | HSE Officer | 16 | — | To Do | High | External auditor
T7-06 | E1 | Mid-project sponsor review | PM | 4 | — | To Do | High | Mo 14 check-in
Sprint 8 ¦ Mo 15–16 ¦ Theme: Pilot Trial Closeout & Gate ¦ Story Points: 31 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T8-01 | E4 | Complete 3-month pilot capture trial | R&D Lead | 24 | — | To Do | Critical | Day 90 shutdown
T8-02 | E4 | Compile pilot performance data report | R&D Lead + PM | 16 | — | To Do | Critical | KPI results vs. targets
T8-03 | E4 | Phase 2 gate review with sponsor | PM | 4 | — | To Do | Critical | Go/No-Go for closeout
T8-04 | E6 | Build economic model (LCOC, NPV) | PM | 24 | — | To Do | Critical | 3 scale scenarios
T8-05 | E5 | Close all regulatory conditions | PM | 8 | — | To Do | Critical | Regulator sign-off
T8-06 | E1 | Monthly sponsor dashboard (Mo 15–16) | PM | 6 | — | To Do | High | Last two dashboard reports
Sprint 9 ¦ Mo 17–18 ¦ Theme: Final Report & Closeout ¦ Story Points: 24 ¦ Status: To Do
Task ID | Epic | Task Description | Owner | Est. Hrs | Actual Hrs | Status | Priority | Notes
T9-01 | E6 | Draft final CCS feasibility report | PM + All Leads | 40 | — | To Do | Critical | 50+ pages integrated report
T9-02 | E6 | Internal peer review of final report | All Leads | 12 | — | To Do | High | Quality check
T9-03 | E6 | Prepare go/no-go board presentation | PM + Sponsor | 16 | — | To Do | Critical | Executive slide deck
T9-04 | E6 | Deliver go/no-go board presentation | PM | 4 | — | To Do | Critical | Board decision
T9-05 | E6 | Lessons learned workshop | PM + Full Team | 8 | — | To Do | Medium | Document & archive
T9-06 | E6 | Project closeout — handover & archive | PM | 8 | — | To Do | Medium | Assets & docs handed over