## Budget Summary
CCS Research Initiative — Budget Summary
Project Duration: 18 months ¦ Total Budget: RM 2,400,000 ¦ Version: 1.0 ¦ Jan 2025
Phase / Work Area | Budget (RM) | % of Total | Q1 (RM) | Q2 (RM) | Q3 (RM) | Notes
1.0 Initiation & Planning | 120000 | 5% | 120000 | 0 | 0 | Charter, lit review, regulatory mapping, vendor selection
2.0 Phase 1 — Bench-Scale R&D | 480000 | 20% | 120000 | 120000 | 240000 | Sorbent screening, bench experiments, Phase 1 report
3.0 Phase 2 — Pilot Plant | 1100000 | 45.83% | 0 | 200000 | 0 | Design, procurement, construction, commissioning, testing
4.0 Geological Storage Survey | 350000 | 14.58% | 0 | 0 | 150000 | Seismic survey, core analysis, storage capacity model
5.0 HSE & Compliance | 150000 | 6.25% | 0 | 50000 | 0 | HAZOP, EIA submission, safety audit, regulatory liaison
6.0 Reporting & Closeout | 200000 | 8.333% | 0 | 0 | 200000 | Final feasibility report, economic model, go/no-go pack
Contingency Reserve (10%) | 240000
Sub-total (excl. contingency) | 2400000
TOTAL PROJECT BUDGET | 2400000
KEY ASSUMPTIONS
• All personnel costs based on fully-loaded day rates (including overhead)
• Equipment procurement assumes fixed-price contracts; 10% contingency held separately
• Geological survey costs based on 3D seismic acquisition + 2 appraisal wells
• Pilot plant CAPEX assumes modular pre-fabricated unit; no civil works included
• Regulatory permit fees (~RM15,000) included under Phase 1 Planning budget
• Budget in USD; no forex adjustment assumed (all vendors in same currency)

## Detailed Budget
CCS Research Initiative — Detailed Budget Breakdown
Blue text = hardcoded input ¦ Black text = formula ¦ Adjust blue cells only
WP Code | Description | Cost Type | Unit Cost (RM) | Units | Total (RM) | Month | Notes
PHASE 1 — INITIATION & PLANNING
WP 1.1 | Project charter & scope document | Labour | 2500 | 2 | 5000 | 1–2 | PM + team leads
WP 1.2 | Literature review — CCS technologies | Labour | 3000 | 3 | 9000 | 1–2 | R&D Lead
WP 1.3 | Regulatory mapping & permits | Professional | 15000 | 1 | 15000 | 1–2 | Legal/regulatory consultant
WP 1.4 | Vendor & partner selection | Labour | 2000 | 3 | 6000 | 1–2 | PM + procurement
WP 1.5 | Risk register v1 workshop | Labour | 1500 | 2 | 3000 | 2 | PM + team
Phase 1 Sub-total
PHASE 2 — BENCH-SCALE R&D
WP 2.1 | Sorbent screening (MEA, MDEA, MOFs) | Lab Materials | 45000 | 1 | 45000 | 3–5 | Reagents, analytical supplies
WP 2.2 | Bench-scale absorption column setup | Equipment | 80000 | 1 | 80000 | 3–4 | Column, pumps, sensors, fittings
WP 2.3 | CO₂ capture experiments | Labour | 6000 | 12 | 72000 | 4–7 | R&D Lead + 2 researchers
WP 2.4 | Sorbent regeneration testing | Labour | 4000 | 8 | 32000 | 5–7 | R&D Lead + Process Eng.
WP 2.5 | Analytical equipment (GC, FTIR) | Equipment | 60000 | 1 | 60000 | 3 | CO₂ purity analysis instruments
WP 2.6 | Phase 1 gate report & review | Labour | 3000 | 3 | 9000 | 8 | PM + R&D Lead
Phase 2 Sub-total
PHASE 3 — PILOT PLANT SCALE-UP
WP 3.1 | Pilot plant engineering design | Professional | 120000 | 1 | 120000 | 9–10 | EPC contractor — fixed scope
WP 3.2 | Equipment procurement | Equipment | 450000 | 1 | 450000 | 10–11 | Absorber, heat exchanger, compressor, tanks
WP 3.3 | Construction & civil works | Professional | 250000 | 1 | 250000 | 11–13 | Modular construction + site prep
WP 3.4 | Commissioning & start-up | Labour | 80000 | 1 | 80000 | 13–14 | Process Eng. + vendor technicians
WP 3.5 | 3-month pilot capture trial | Labour | 90000 | 1 | 90000 | 13–15 | Operators + data collection team
WP 3.6 | Utilities & consumables | Operating | 60000 | 1 | 60000 | 13–15 | Power, steam, solvent make-up
WP 3.7 | Phase 2 gate report & review | Labour | 4000 | 3 | 12000 | 15 | PM + core team
Phase 3 Sub-total
PHASE 4 — GEOLOGICAL STORAGE SURVEY
WP 4.1 | 3D seismic data acquisition | Professional | 150000 | 1 | 150000 | 6–9 | Geophysical survey contractor
WP 4.2 | Core sampling & well analysis | Professional | 80000 | 1 | 80000 | 9–11 | Laboratory petrophysical analysis
WP 4.3 | CO₂ plume migration simulation | Software/Lab | 40000 | 1 | 40000 | 11–13 | Reservoir simulator license + runs
WP 4.4 | Storage feasibility report | Labour | 8000 | 2 | 16000 | 14 | Geoscience Eng. + PM
Phase 4 Sub-total
PHASE 5 — HSE & COMPLIANCE
WP 5.1 | HAZOP study (pre-commissioning) | Professional | 35000 | 1 | 35000 | 12 | HAZOP facilitator + core team
WP 5.2 | Environmental Impact Assessment | Professional | 55000 | 1 | 55000 | 12–15 | EIA consultant
WP 5.3 | HSE audit & safety inspection | Labour | 15000 | 2 | 30000 | 14–16 | HSE Officer + external auditor
WP 5.4 | Regulatory compliance reporting | Labour | 5000 | 3 | 15000 | 15–16 | PM + Legal
Phase 5 Sub-total
PHASE 6 — REPORTING & CLOSEOUT
WP 6.1 | Economic model & cost analysis | Labour | 25000 | 1 | 25000 | 16–17 | PM + financial analyst
WP 6.2 | Final CCS feasibility report | Labour | 20000 | 2 | 40000 | 17–18 | PM + all leads
WP 6.3 | Go/no-go stakeholder presentation | Labour | 8000 | 2 | 16000 | 18 | PM + Sponsor
WP 6.4 | Project closeout & archiving | Labour | 7000 | 2 | 14000 | 18 | PM
Phase 6 Sub-total
TOTAL (excl. contingency) |  |  |  |  | =

## Monthly Cash Flow
CCS Research Initiative — Monthly Cash Flow Forecast (RM)
Phase / Cost Category | Mo 1 | Mo 2 | Mo 3 | Mo 4 | Mo 5 | Mo 6 | Mo 7 | Mo 8 | Mo 9 | Mo 10 | Mo 11 | Mo 12 | Mo 13 | Mo 14 | Mo 15 | Mo 16 | Mo 17 | Mo 18 | Total
Initiation & Planning | 60000 | 60000 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 120000
Phase 1 — Bench R&D | - | - | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | - | - | - | - | - | - | - | - | - | - | 480000
Phase 2 — Pilot Plant | - | - | - | - | - | - | - | - | 122222 | 122222 | 122222 | 122222 | 122222 | 122222 | 122222 | - | - | - | 855554
Geological Survey | - | - | - | - | - | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | 43750 | - | - | - | - | - | - | 306250
HSE & Compliance | - | - | - | - | - | - | - | - | - | - | - | 37500 | 37500 | 37500 | 37500 | - | - | - | 150000
Reporting & Closeout | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | 66667 | 66667 | 66667 | 200001
Monthly Total Spend (RM) | 60000 | 60000 | 80000 | 80000 | 80000 | 123750 | 123750 | 123750 | 165972 | 165972 | 165972 | 203472 | 159722 | 159722 | 159722 | 66667 | 66667 | 66667 | 2111805
Cumulative Spend (RM) | 60000 | 120000 | 200000 | 280000 | 360000 | 483750 | 607500 | 731250 | 897222 | 1063194 | 1229166 | 1432638 | 1592360 | 1752082 | 1911804 | 1978471 | 2045138 | 2111805

## Budget Tracker
CCS Research Initiative — Budget Tracker (Monthly Update)
Update the 'Actual Spend (RM)' column each month. All variance calculations are automatic.
WP Code | Work Package | Planned Budget (RM) | Actual Spend (RM) | Variance (RM) | Var % | Status
WP 1.1–1.5 | Initiation & Planning | 120000 | 0 | 120000 | 100% | Over budget
WP 2.1–2.6 | Phase 1 — Bench-Scale R&D | 480000 | 0 | 480000 | 100% | Over budget
WP 3.1–3.7 | Phase 2 — Pilot Plant Scale-Up | 1100000 | 0 | 1100000 | 100% | Over budget
WP 4.1–4.4 | Geological Storage Survey | 350000 | 0 | 350000 | 100% | Over budget
WP 5.1–5.4 | HSE & Compliance | 150000 | 0 | 150000 | 100% | Over budget
WP 6.1–6.4 | Reporting & Closeout | 200000 | 0 | 200000 | 100% | Over budget
TOTAL | All Work Packages | 2400000 | 0 | 2400000 | 100%