Communication Management Plan

Carbon Capture & Storage (CCS) Research Initiative

Project Manager: Harissa Rania  |   Version: 1.0   |   Date: January 2025   |   Status: Active

# 1. Purpose & Objectives

This Communication Management Plan defines how project information will be planned, structured, monitored, and distributed throughout the 18-month CCS Research Initiative. It ensures all stakeholders receive timely, relevant, and accurate project updates in the appropriate format.

Key objectives of this plan:

- Ensure consistent, transparent communication across all project phases

- Define clear communication channels and frequency for each stakeholder group

- Establish escalation procedures for issues and risks

- Support informed decision-making at each phase gate review

- Maintain regulatory compliance through formal documentation protocols

# 2. Communication Matrix

The table below defines the full communication schedule for all stakeholder groups, including channel, frequency, owner, and content focus.

| Stakeholder | Communication type | Channel | Owner | Frequency | Content / focus |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor / Exec | Monthly dashboard report | Email + PDF | PM | Monthly (1st Monday) | High-level progress, budget, risks, decisions needed |
| R&D Lead (Chemistry) | Daily standup + phase reports | In-person / Teams | PM | Daily (9:00 AM) | Experiment progress, blockers, sorbent results |
| Process Engineer | Daily standup + design reviews | In-person / Teams | PM | Daily (9:00 AM) | Design milestones, procurement, pilot commissioning |
| Geoscience Engineer | Weekly update + survey reports | Email + Teams | PM | Weekly (Friday) | Geological survey status, site suitability findings |
| HSE Officer | Bi-weekly safety review | In-person | PM + HSE | Bi-weekly (Wednesday) | Safety incidents, hazard log, compliance checklist |
| Regulatory Authority | Formal permit submissions | Official letter / Email | PM + Legal | As required | Permit applications, EIA submissions, compliance updates |
| Community Liaison Officer | Quarterly public briefing | Public meeting / Email | PM + Comms | Quarterly | Project overview, safety data, community Q&A |
| Full Project Team | Weekly team meeting | In-person / Teams | PM | Weekly (Monday 10 AM) | Status, priorities, cross-team dependencies |

# 3. Meetings & Events Schedule

Recurring and milestone-based meetings are defined below with attendees, duration, and purpose.

| Meeting | When | Attendees | Duration | Agenda focus |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | Month 1, Week 1 | All stakeholders | 3 hours | Introduce project, confirm scope, assign responsibilities, establish communication norms |
| Weekly Team Standup | Every Monday 9:00 AM | Core team (12 FTEs) | 30 min | Progress update, blockers, priorities for the week |
| Gate Review — Phase 1 | End of Month 8 | Core team + Sponsor | 2 hours | Review bench-scale results, approve go/no-go to Phase 2 |
| Gate Review — Phase 2 | End of Month 15 | Core team + Sponsor + HSE | 3 hours | Review pilot plant results, approve go/no-go to closeout |
| Monthly Sponsor Report | 1st Monday of each month | PM + Sponsor | 45 min | Budget, schedule, risk dashboard, strategic decisions |
| Bi-weekly HSE Review | Every other Wednesday | PM + HSE + Engineers | 1 hour | Safety audit, incident log, corrective actions |
| Geological Survey Review | Monthly (Phase 4 active) | PM + Geoscience Eng. | 1 hour | Survey progress, preliminary findings, site suitability |
| Lessons Learned Workshop | Month 17 | Full project team | 3 hours | Capture learnings from all phases for final closeout report |

# 4. Reporting Structure

## 4.1 Monthly Sponsor Dashboard

Delivered on the 1st Monday of each month. Includes:

- Overall RAG status (Red / Amber / Green) for scope, schedule, budget, and risk

- Key achievements in the past month

- Planned activities for the coming month

- Budget variance vs. plan (updated monthly)

- Top 3 active risks with mitigation status

- Decisions or approvals required from the Sponsor

## 4.2 Phase Gate Reports

Produced at the end of Phase 1 (Month 8) and Phase 2 (Month 15). Each gate report includes:

- Summary of phase deliverables and outcomes vs. planned objectives

- Technical performance data (capture efficiency, energy penalty, etc.)

- Budget actuals vs. plan for the phase

- Risk register update

- Go / No-Go recommendation with supporting rationale

- Proposed plan for the next phase

## 4.3 Final Feasibility Report

Delivered at the end of Month 18. The final report integrates all phase findings into a comprehensive CCS feasibility assessment, including an economic model and a board-ready go/no-go recommendation for commercial-scale development.

# 5. Escalation Matrix

The escalation matrix defines how issues are raised and resolved at each level of the organization.

| Escalation level | Trigger condition | Escalation path | Response time |
| --- | --- | --- | --- |
| Level 1 — Team | Task-level issue, minor schedule slippage (< 1 week) | Team member → R&D / Process Lead | 24 hours |
| Level 2 — PM | Budget variance > 5%, schedule slippage > 2 weeks, technical blocker | Lead → Project Manager | 48 hours |
| Level 3 — Sponsor | Budget overrun > 10%, scope change, regulatory non-compliance | PM → Project Sponsor | 72 hours |
| Level 4 — Executive | Project cancellation risk, legal issue, major HSE incident | Sponsor → Executive Committee | Immediate |

# 6. Document Management

All project documents will be stored in a centralized SharePoint folder with version-controlled naming: [ProjectCode]_[DocType]_v[X.X]_[YYYYMMDD]. Access will be role-based. Key document types include:

- Project Charter and Baseline Plan (read-only for all; editable by PM only)

- Phase reports and gate review packs (archived after each gate)

- Risk register (updated monthly by PM)

- Lab notebooks and experimental data (owned by R&D Lead, backed up weekly)

- Regulatory submissions and correspondence (owned by PM + Legal)

- HSE incident log (owned by HSE Officer; restricted access)

# 7. Communication Tools

| Tool | Purpose | Used by |
| --- | --- | --- |
| Microsoft Teams | Daily standups, team chat, video calls | Core team (12 FTEs) |
| SharePoint | Document management and version control | All stakeholders |
| Asana / Trello | Task tracking, WBS management, milestone tracking | Core team |
| Email (Outlook) | Formal communications, sponsor reports, regulatory submissions | All stakeholders |
| MS Excel / Power BI | Budget tracking, KPI dashboards | PM + Sponsor |
| Zoom / Teams Video | Remote meetings with external partners and regulators | PM + relevant leads |

# 8. Plan Approval

This Communication Management Plan has been reviewed and approved by the following:

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager |  |  |  |
| R&D Lead |  |  |  |
| HSE Officer |  |  |  |
| Project Sponsor |  |  |  |