Risk Management Plan

Carbon Capture & Storage (CCS) Research Initiative

| Project Title | CCS Research Initiative |
| --- | --- |
| Document Version | 1.0 |
| Prepared By | HARISSA RANIA — Project Manager |
| Date | January 2025 |
| Project Duration | 18 Months (January 2025 – June 2026) |
| Total Budget | RM2,400,000 Malaysia Ringgit |

# 1. Purpose

This Risk Management Plan (RMP) defines how risks will be identified, analyzed, prioritized, responded to, and monitored throughout the CCS Research Initiative. It provides a structured framework to proactively protect project objectives — scope, schedule, budget, and quality — from uncertainty and adverse events.

# 2. Risk Management Approach

## 2.1 Risk Philosophy

This project adopts a proactive risk management approach. Risks are identified early, tracked continuously, and owned by named team members. The guiding principle is: all identifiable risks must have a documented mitigation strategy before work begins on the related work package.

## 2.2 Risk Tolerance

The project sponsor has defined the following risk tolerance thresholds:

- Schedule: Tolerance of up to 2 weeks slippage per phase without escalation. Beyond 2 weeks requires Sponsor notification.

- Budget: Tolerance of ±5% variance per phase. Variance >10% requires Sponsor approval for corrective action.

- Quality: Zero tolerance for HSE incidents (LTI). Any safety incident triggers an immediate stop-work review.

- Regulatory: Zero tolerance for non-compliance. Any regulatory breach triggers immediate escalation to Sponsor and legal counsel.

# 3. Risk Management Process

## 3.1 Risk Identification

Risks are identified through the following methods:

- Kick-off risk workshop at project start (all core team members)

- Phase-start risk reviews before each new phase begins

- Weekly team standup — standing agenda item for new risk identification

- Phase gate reviews — retrospective risk assessment

- Expert interviews (HSE Officer, Geoscience Engineer, regulatory consultant)

- Lessons learned review from comparable CCS and chemical process projects

## 3.2 Risk Analysis — Probability & Impact Matrix

Each risk is scored on two dimensions (1–5 scale). Risk Score = Probability × Impact.

| Score | Probability | Impact | Risk Level |
| --- | --- | --- | --- |
| 1 | Rare (<10%) | Negligible | Very Low (1–4) |
| 2 | Unlikely (10–30%) | Minor | Low (5–8) |
| 3 | Possible (30–50%) | Moderate | Medium (9–12) |
| 4 | Likely (50–70%) | Significant | High (13–16) |
| 5 | Almost Certain (>70%) | Severe | Critical (17–25) |

## 3.3 Risk Response Strategies

- Avoid: Eliminate the risk by changing the project plan or approach

- Mitigate: Reduce the probability or impact of the risk

- Transfer: Shift the risk to a third party (e.g., insurance, fixed-price contracts)

- Accept: Acknowledge the risk and monitor it; create a contingency plan

# 4. Risk Register Summary

The full risk register is maintained as a living document and reviewed at every weekly team meeting. Below are the top risks at project initiation:

| ID | Risk Description | Prob. | Impact | Score | Response | Mitigation Action |
| --- | --- | --- | --- | --- | --- | --- |
| R-01 | Sorbent degradation reduces capture efficiency | 3 | 4 | 12 | Mitigate | Test stability over 500 hrs; MEA fallback sorbent pre-selected |
| R-02 | Regulatory permit delays stall Phase 1 | 3 | 3 | 9 | Mitigate | Engage regulator in Month 1; fast-track application submitted |
| R-03 | Geological site unsuitable for CO2 storage | 2 | 5 | 10 | Avoid | Identify 2 candidate sites; pre-screening before survey commitment |
| R-04 | Pilot plant cost overrun from equipment prices | 3 | 4 | 12 | Transfer | Fixed-price EPC contract; 10% contingency reserve held by PM |
| R-05 | Key team member departure | 2 | 3 | 6 | Mitigate | Cross-train 2 staff per critical role; all procedures documented |
| R-06 | HSE incident during commissioning | 2 | 5 | 10 | Mitigate | HAZOP mandatory; emergency response plan; stop-work authority |
| R-07 | CO2 capture efficiency below 90% target | 3 | 4 | 12 | Mitigate | Iterative process optimization; column redesign contingency |
| R-08 | Community opposition to storage site | 2 | 3 | 6 | Accept | Early community engagement; quarterly public briefings |
| R-09 | Amine sorbent corrosion damages equipment | 2 | 4 | 8 | Mitigate | Use corrosion-resistant materials; monitor pH continuously |
| R-10 | Data loss from lab equipment failure | 2 | 3 | 6 | Mitigate | Daily data backup to SharePoint; redundant measurement devices |

# 5. Roles & Responsibilities

| Role | Risk Management Responsibility |
| --- | --- |
| Project Manager | Owns the risk register; facilitates risk workshops; reports top risks in monthly dashboard; escalates critical risks to Sponsor |
| Project Sponsor | Reviews risk dashboard monthly; approves risk response for high/critical risks; authorizes use of contingency reserve |
| R&D Lead | Identifies and owns technical R&D risks; updates risk status weekly in standup |
| Process Engineer | Identifies and owns engineering and commissioning risks; signs off HAZOP actions |
| HSE Officer | Identifies and owns all safety and environmental risks; authority to stop work if safety risk is unacceptable |
| Geoscience Engineer | Identifies and owns geological storage risks; updates risk register after each survey milestone |
| All Team Members | Raise new risks at weekly standup; report near-misses and emerging issues immediately to PM |

# 6. Risk Monitoring & Reporting

- Risk register reviewed at every weekly team standup (standing agenda item)

- Top 3 risks reported in monthly sponsor dashboard with RAG status

- Full risk register reviewed and updated at each phase gate

- New risks can be submitted by any team member at any time via the risk log in SharePoint

- Risks that become issues (i.e., materialize) are escalated per the Escalation Matrix in the Communication Plan

# 7. Contingency Reserve

A 10% contingency reserve ($240,000) is held by the Project Manager. Drawdown requires written approval from the Project Sponsor and must be documented with justification. Remaining contingency is reported monthly.

# 8. Document Control

| Document Owner | Project Manager |
| --- | --- |
| Review Frequency | Monthly (full review at each gate) |
| Storage Location | SharePoint > CCS Project > Risk Management |
| Next Review Date | February 2025 |