## Risk Register
RISK REGISTER — CCS Research Initiative
Risk levels: High (Red) ¦ Medium (Orange) ¦ Low (Green) ¦ All risks tracked monthly
Risk ID | Description | Probability | Impact | Risk Level | Mitigation Strategy | Owner
R-01 | Sorbent degradation reduces capture efficiency over time | Medium | High | High | Test sorbent stability over 500 hrs; select proven MEA baseline as fallback | R&D Lead
R-02 | Regulatory permit delays stall Phase 1 start | Medium | Medium | Medium | Engage regulatory body in Month 1; fast-track permit application | Project Manager
R-03 | Geological site proves unsuitable for storage | Low | Very High | High | Identify 2 candidate sites; run preliminary screening before committing | Geoscience Eng.
R-04 | Pilot plant cost overrun due to equipment price increases | Medium | High | High | Lock in fixed-price contracts; hold 10% contingency reserve | Project Manager
R-05 | Key team member departure disrupts R&D continuity | Low | Medium | Medium | Cross-train at least two staff per critical workstream; document all procedures | Project Manager
R-06 | HSE incident during pilot plant commissioning | Low | Very High | High | Mandatory HAZOP before commissioning; emergency response plan in place | HSE Officer
R-07 | CO₂ capture efficiency below 90% target at pilot scale | Medium | High | High | Optimize process conditions iteratively; consider column redesign if needed | Process Eng.
R-08 | Community opposition to geological storage site | Low | Medium | Low | Early community engagement; transparent communication of safety data | Community Officer
RISK SUMMARY
High Risks | 4 | Medium Risks | 2 | Low Risks | 1