## WBS
WORK BREAKDOWN STRUCTURE — CCS Research Initiative
Project: Carbon Capture & Storage (CCS) Research Initiative ¦ Duration: 18 months ¦ Budget: $2,400,000
WBS Code | Work Package / Task | Description | Owner | Start Mo. | End Mo. | Duration (Mo.)
1.0 — Initiation & Planning (Month 1–2)
WP 1.1 | Project charter | Define scope, objectives, budget and team structure | Project Manager | 1 | 2 | 2
WP 1.2 | Literature review | Survey existing CCS technologies and sorbents | R&D Lead | 1 | 2 | 2
WP 1.3 | Regulatory mapping | Identify permits, standards (ISO 27914, local EIA law) | Project Manager | 1 | 2 | 2
WP 1.4 | Vendor & partner selection | Geological survey firm, lab equipment suppliers | Project Manager | 1 | 2 | 2
WP 1.5 | Risk register v1 | Initial risk identification and mitigation planning | Project Manager | 1 | 2 | 2
2.0 — Phase 1: Bench-Scale R&D (Month 3–8)
WP 2.1 | Sorbent screening | Test MEA, MDEA, ionic liquids, MOFs for CO₂ uptake | R&D Lead | 3 | 5 | 3
WP 2.2 | Bench-scale setup | Design and build absorption column (lab scale) | Process Engineer | 3 | 6 | 4
WP 2.3 | Capture experiments | Run trials with simulated flue gas at varying conditions | R&D Lead | 5 | 8 | 4
WP 2.4 | Regeneration testing | Assess energy penalty for sorbent regeneration | R&D Lead | 6 | 8 | 3
WP 2.5 | Phase 1 report & gate review | Data analysis, sorbent selection, gate review | Project Manager | 8 | 8 | 1
3.0 — Phase 2: Pilot Plant Scale-Up (Month 9–15)
WP 3.1 | Pilot plant design | Engineering design for 500 tonne/yr pilot unit | Process Engineer | 9 | 11 | 3
WP 3.2 | Procurement | Purchase equipment: absorber column, heat exchanger, compressor | Project Manager | 9 | 11 | 3
WP 3.3 | Construction & commissioning | Build, install, and commission pilot plant on site | Process Engineer | 11 | 13 | 3
WP 3.4 | Pilot testing | Run 3-month continuous capture trial; collect performance data | Process Engineer | 13 | 15 | 3
WP 3.5 | HSE audit | Safety inspection and environmental compliance check | HSE Officer | 12 | 15 | 4
4.0 — Geological Storage Assessment (Month 6–14)
WP 4.1 | Seismic survey | 3D seismic data acquisition at candidate storage site | Geoscience Eng. | 6 | 9 | 4
WP 4.2 | Core & well analysis | Reservoir porosity, permeability, and caprock integrity | Geoscience Eng. | 9 | 12 | 4
WP 4.3 | Storage capacity model | Numerical simulation of CO₂ plume migration | Geoscience Eng. | 11 | 14 | 4
WP 4.4 | Storage feasibility report | Final geological suitability assessment | Geoscience Eng. | 14 | 14 | 1
5.0 — Reporting & Closeout (Month 16–18)
WP 5.1 | Economic model | Levelized cost of capture, NPV analysis at commercial scale | Project Manager | 16 | 17 | 2
WP 5.2 | Final feasibility report | Integrated capture + storage + economic findings | Project Manager | 16 | 18 | 3
WP 5.3 | Go/no-go recommendation | Stakeholder presentation and decision package | Project Manager | 18 | 18 | 1
WP 5.4 | Project closeout | Lessons learned, asset handover, team disbandment | Project Manager | 18 | 18 | 1

## Schedule
PROJECT SCHEDULE — CCS Research Initiative (18-Month Gantt)
Jan 2025 – Jun 2026 ¦ Shaded cells = active phase ¦ Milestone = key gate/decision
Phase / Deliverable | Details | Budget | Milestone | Jan '25 | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan '26 | Feb | Mar | Apr | May | Jun '26
Initiation & Planning | Charter, lit review, regulatory | RM120K | Kick-off + permits | █ | █
Phase 1: Bench R&D | Sorbent screening & experiments | RM480K | Gate review 1 (Mo 8) |  |  | █ | █ | █ | █ | █ | █
Geological Survey | Seismic, core, capacity model | RM350K | Storage report (Mo 14) | [5 empty] | █ | █ | █ | █ | █ | █ | █ | █ | █
Phase 2: Pilot Plant | Design, build, commission, test | RM1,100K | Gate review 2 (Mo 15) | [8 empty] | █ | █ | █ | █ | █ | █ | █
HSE & Compliance | Safety audit, EIA submission | RM150K | EIA approval (Mo 16) | [11 empty] | █ | █ | █ | █ | █
Reporting & Closeout | Final report, go/no-go decision | RM200K | Go/no-go decision (Mo 18) | [15 empty] | █ | █ | █
TOTAL BUDGET
LEGEND
Initiation & Planning
Phase 1 Bench R&D
Geological Storage
Phase 2 Pilot Plant
HSE & Compliance
Reporting & Closeout

## Stakeholders
STAKEHOLDER REGISTER — CCS Research Initiative
Interest & Influence ratings: Low ¦ Medium ¦ High ¦ Very High
Initials | Name / Role | Responsibilities | Interest | Influence | Category | Communication Strategy | Frequency
PM | Project Manager | Overall coordination & delivery | High | High | Lead | Daily standup, weekly status report | Daily
RD | R&D Lead (Chemistry) | Sorbent selection & bench testing | High | High | Core Team | Daily, part of core team | Daily
PE | Process Engineer | Pilot plant design & scale-up | High | High | Core Team | Daily during Phase 2 | Daily / Phase 2
GE | Geoscience Engineer | Geological site survey & storage | High | Medium | Core Team | Weekly, phase 4 reports | Weekly
HS | HSE Officer | Safety compliance & risk management | Medium | High | Support | Bi-weekly safety reviews | Bi-weekly
SP | Sponsor / Exec | Budget approval & strategic direction | Medium | Very High | Sponsor | Monthly dashboard report | Monthly
RA | Regulatory Authority | Environmental permits & ISO compliance | Low | Very High | External | Formal submissions, as required | As required
CO | Community Officer | Local community liaison | Low | Medium | External | Quarterly public briefings | Quarterly

## Risk Register
RISK REGISTER — CCS Research Initiative
Risk levels: High (Red) ¦ Medium (Orange) ¦ Low (Green) ¦ All risks tracked monthly
Risk ID | Description | Probability | Impact | Risk Level | Mitigation Strategy | Owner
R-01 | Sorbent degradation reduces capture efficiency over time | Medium | High | High | Test sorbent stability over 500 hrs; select proven MEA baseline as fallback | R&D Lead
R-02 | Regulatory permit delays stall Phase 1 start | Medium | Medium | Medium | Engage regulatory body in Month 1; fast-track permit application | Project Manager
R-03 | Geological site proves unsuitable for storage | Low | Very High | High | Identify 2 candidate sites; run preliminary screening before committing | Geoscience Eng.
R-04 | Pilot plant cost overrun due to equipment price increases | Medium | High | High | Lock in fixed-price contracts; hold 10% contingency reserve | Project Manager
R-05 | Key team member departure disrupts R&D continuity | Low | Medium | Medium | Cross-train at least two staff per critical workstream; document all procedures | Project Manager
R-06 | HSE incident during pilot plant commissioning | Low | Very High | High | Mandatory HAZOP before commissioning; emergency response plan in place | HSE Officer
R-07 | CO₂ capture efficiency below 90% target at pilot scale | Medium | High | High | Optimize process conditions iteratively; consider column redesign if needed | Process Eng.
R-08 | Community opposition to geological storage site | Low | Medium | Low | Early community engagement; transparent communication of safety data | Community Officer
RISK SUMMARY
High Risks | 4 | Medium Risks | 2 | Low Risks | 1

## KPIs
KEY PERFORMANCE INDICATORS — CCS Research Initiative
KPIs tracked throughout the 18-month project lifecycle. Blue = target fill % ¦ Green = on track ¦ Orange = at risk
KPI | Target | Baseline | Progress (%) | Status | Notes
CO₂ capture efficiency | ≥ 90% | 70% (industry avg) | 90% | Target | Measured at pilot scale steady state
Levelized cost of capture | ≤ RM60/tonne | RM80–100/tonne | 60% | Target | Based on pilot OPEX + CAPEX model
Sorbent regeneration energy | ≤ 3.5 GJ/tonne CO₂ | 4.0 GJ/tonne | 75% | On Track | Key driver of operating cost
Schedule adherence | ≥ 90% milestones on time | Baseline: 100% | 100% | On Track | Tracked at each gate review
Budget variance | ≤ ±5% | RM2.4M approved | 95% | On Track | Reviewed monthly vs. plan
HSE incidents (LTI) | 0 lost-time incidents | Zero tolerance | 100% | On Track | Tracked weekly; stop-work authority in place
Geological storage capacity | ≥ 1 Mt CO₂ confirmed | TBD by survey | 50% | At Risk | Confirmed after Phase 4 survey
Sorbent cycle lifetime | ≥ 1000 cycles | 500 cycles (MEA) | 65% | On Track | Accelerated cycle testing in bench phase